## Classification totals
PMTwin requirement classification totals
Review date | 2026-10-03
Repository HEAD inspected | d113b3b9a4da198d7c2f872d465b805730e1ce55
Deployed UAT version | Deployed UAT version not verified
These totals are rows in this workbook, not a claim that every product behaviour was re-tested.
Code | Classification | Rows
1 | 1. Implemented and verified | 0
2 | 2. Implemented but not sufficiently verified | 20
3 | 3. Partially implemented original requirement | 8
4 | 4. Original requirement not found in the reviewed implementation | 2
5 | 5. Defect against a confirmed requirement | 0
6 | 6. Documented approved deferral | 0
7 | 7. Clarification or conflicting specifications | 21
8 | 8. Proposed change requiring scope confirmation | 9
9 | 9. Approved change request | 0
Total |  | 60

## Traceability
Requirement ID | Business requirement | Original source | Later amendments and approval evidence | Current implementation reference | Implementation status | Verification status | UAT relevance | Gap or conflict | Technical impact | Recommended classification | Decision or next action | Proposed owner role
REQ-001 | Needs and Offers are both first-class posts, not a job board plus a profile. | PDF 10 Jan 2025, pages 2–3, Need/Offer Framework. | No approved amendment found. Internal BRD FR-10 (repo BRD/08, updated note 2025-03-07) restates post-to-post matching. BRD is not a signed client baseline. | web/src/types/enums.ts OpportunityIntent; web/src/domain/intent.ts toCanonicalIntent; packages/commands opportunity intent payload. | Need, offer, and hybrid exist on the domain entity. The create draft type is need or offer only. | Code inspection 3 Oct 2026. Tests not re-executed. Browser not re-run. | UAT posting scripts exist for need and offer. Hybrid posting was not re-tested. | A single opportunity can store hybrid, but the wizard command path omits hybrid. Separate linked posts are not the same thing. | UI; domain/data; matching | 3. Partially implemented original requirement | Confirm whether one opportunity may carry both sides, or only separate posts may be linked. | Client product owner; engineering
REQ-002 | Semantic mirroring: Required Skills becomes Available Skills, Budget becomes Rate, and the same model is used on both sides. | PDF 10 Jan 2025, page 3. | No approved amendment found. | web/src/config/need-offer-framework.ts attribute pairs; web/src/lib/need-offer-semantic-read-model.ts; draft-model.ts stores offeredSkills for offers and requiredSkills for needs. | Display labels mirror. Persisted skill field is offeredSkills, not availableSkills. | Code inspection only. | Relevant to match explanations and reload. | Label and storage name differ. One shared attribute bag can still overwrite a side if new dropdowns are written into it. | UI; domain/data; matching | 3. Partially implemented original requirement | Keep separate need-side and offer-side fields through save, reload, publish, match, and display. | Engineering; client product owner
REQ-003 | Five main collaboration families. | PDF 10 Jan 2025, page 2. Detailed spec Model Hierarchy: Project-Based, Strategic Partnerships, Resource Pooling, Hiring, Competition. | No approval found for renaming families to cash_subcontracting, service_exchange, joint_venture, resource_sharing, and hiring. | packages/collaboration-models/src/registry/registry-data.ts MAIN_MODEL_REGISTRY (five keys). | Five families are stored. Names and membership differ from the detailed spec, notably Competition folded toward cash subcontracting and Co-ownership absent. | Code inspection. Registry tests exist and were not re-run. | High. Model mismatch is a hard match rejection. | Family names are an internal taxonomy. They are not the eight cards in the August 2026 workbooks. | Domain/data; matching; UI | 3. Partially implemented original requirement | Do not replace the five families until a mapping decision is approved. UI labels can differ from stored keys. | Client product owner
REQ-004 | Headline count of 15 collaboration models. | PDF 10 Jan 2025, page 2. The ten pages do not name 15 models. | Detailed specification enumerates 13 sub-models. No document explains the two-model difference or approves either count. | SUB_MODEL_REGISTRY has 13 keys, with a different membership from the specification's 13. | Neither 15 named models nor an approval of the drop from 15 to 13 was found. | Source inspection. Not a test result. | Taxonomy baseline is ambiguous before any wireframe change. | 15, 13-as-specified, and 13-as-implemented are three different sets. | Domain/data | 7. Clarification or conflicting specifications | Ask the client to confirm the authoritative model list. Do not treat the headline 15 as cancelled. | Client product owner
REQ-005 | Thirteen named sub-models in the detailed specification, including Co-Ownership Pooling and excluding a separate Equipment Sharing sub-model. | web/pmtwin_collaboration_models_final.docx (file date 23 Dec 2025) and the repository markdown conversion. Contents: 1.1 Task-Based, 1.2 Consortium, 1.3 Project JV, 1.4 SPV, 2.1 Strategic JV, 2.2 Strategic Alliance, 2.3 Mentorship, 3.1 Bulk Purchasing, 3.2 Co-Ownership Pooling, 3.3 Resource Sharing and Exchange, 4.1 Professional Hiring, 4.2 Consultant Hiring, 5.1 Competition/RFP. | Filename 'final' and the converter prefix are not approval. No change approval was found that replaced 3.2 with equipment_sharing. | registry-data.ts keys listed above except co_ownership; equipment_sharing is present and resource_sharing is separate. | Twelve specification names exist as keys. Co-ownership does not. Equipment sharing was added as its own key. | Code inspection. | Existing opportunities, matches, and agreements use these keys. | Hiding sub-models in the UI is possible only if the stored key remains. Deleting keys would break hard compatibility and history. | Domain/data; matching; lifecycle | 3. Partially implemented original requirement | Retain every current key until an approved map says retain, alias, or retire. Do not retire Consortium, Project JV, SPV, Strategic JV, Strategic Alliance, or Competition/RFP by assumption. | Client product owner; engineering
REQ-006 | Co-ownership records asset, owner count, equity, investment, ongoing costs, usage, maintenance, insurance, exit, and dispute terms, and matches on capacity, usage, proximity, reliability, and maintenance. | Detailed specification section 3.2, Sub-Model 3.2 Co-Ownership Pooling. PDF page 8 lists Co-Ownership Pooling as a group-formation use case. | No approved deferral of section 3.2 was found. August 2026 Co-ownership card is a later proposal, not the origin of the topic. | equipment_sharing attributes in legacy-attributes.ts: assetDescription, assetType, assetLocation, availability, usageSchedule (Rotation, Booking System, Priority by Ownership %). No co_ownership key. No purchase price, owner count, equity per owner, initial investment, ongoing cost objects, cost sharing, maintenance responsibility, insurance, exit, or dispute fields. | Partial. Usage rule can be recorded as an enum, including the words Booking System. That is not a booking product. Financial terms are not executed as purchases or settlements. | Code inspection. No co-ownership UAT script found. | Material original gap and the subject of a new card. | Equipment sharing covers shared equipment use. It does not cover real-estate or company-stake co-ownership proposed in the workbook. | Domain/data; matching; commercial | 3. Partially implemented original requirement | Complete the original equipment co-ownership record as original scope once the client confirms the specification is binding. Treat real estate, company shares, and pool operations as separate confirmation items. | Client product owner; engineering
REQ-007 | Five value-exchange modes: Cash, Equity, Profit-Sharing, Barter, Hybrid. | PDF 10 Jan 2025, page 4. | Handover states Revenue Sharing is a component and can derive Hybrid, not a sixth mode. No client approval of that sentence was in the file set. | packages/collaboration-models/src/types.ts ExchangeMode. web commercial components add revenue_sharing and custom. legacy-migration.ts deriveLegacyExchangeMode. | The five modes exist. Hybrid is derived when more than one component is enabled, and also when the only component is revenue sharing or custom. | Code inspection. Validation tests exist and were not re-run. Handover claims browser checks for equity, profit sharing, hybrid, and custom. | ISS-04, ISS-05, ISS-06, ISS-08, ISS-15. | A single Custom component is stored as hybrid. That exception is an implementation choice, not a PDF rule. | Commercial; validation | 2. Implemented but not sufficiently verified | Keep five modes. Confirm whether a lone Custom or lone Revenue Sharing component should remain hybrid. | Client product owner; engineering
REQ-008 | After Barter is selected, an offer register opens so the user can select or add an offer. One Need can be linked to multiple Offers. | PDF 10 Jan 2025, page 4 and page 9. | Workbook Step1-Details A23 proposes a narrower case: different-model need and offer become two posts linked at Step 4. That is not the same as the general register. | findOffersForNeedPure can score many offer candidates. No user-facing offer register or explicit need-to-offer link object was found in the reviewed web create flow. | Automatic multi-candidate discovery exists. User linking does not. | Code inspection. | Matching explanations can show multiple candidates. They are not a user-authored link. | Do not classify linking as new. Classify the missing register as an original gap. Classify different-model linking as a new proposal. | UI; matching; domain/data | 4. Original requirement not found in the reviewed implementation | Specify the register and same-model links as original completion. Decide separately whether a link may cross models. | Client product owner; engineering
REQ-009 | Four matching types: one-way, two-way dependency, group formation, and circular exchange of at least three parties. | PDF 10 Jan 2025, pages 5–9. Internal BRD FR-10 names the same four post-to-post routes. | No approved reduction found. Workbooks relabel types and sometimes call a both-sides post Type 4. | packages/matching/src/routing/detect-model.ts; one-way.ts; circular.ts minCycleLength default 3; consortium model. | All four engines exist. Circular is routed only for resource_sharing and equipment_sharing. A type label in the workbook is not a discovered match. | Engine tests exist (models.test.js 3-party cycle) and were not re-run. | Core UAT matching scripts cover four types as internal checklists. | Office, excavator, and accounting examples succeed only if each post is compatible under the current sub-model and role rules. Mixed sub-models are hard-incompatible. | Matching | 3. Partially implemented original requirement | Preserve four engines. Decide whether the PDF examples must match across sub-models. | Client product owner; engineering
REQ-010 | Example score: attribute overlap 40%, budget 30%, timeline 15%, location 10%, reputation 5%, illustrated total 82%. | PDF 10 Jan 2025, page 6. Presented as a match-score example, not as a signed formula clause. | Live weights differ. docs/uat/uat-findings-log.md UAT-26 records the split and classifies it as needing a product decision. No approval of either profile was found. | packages/matching/src/config/defaults.ts DEFAULT_WEIGHTS 25/20/20/10/10/10/5 plus ATTRIBUTE_OVERLAP 0.25 legacy alias. scorePair adds category bonus and caps at 1. | Implemented profile is the seven-factor profile, not the PDF example. | Code inspection. UAT-26 was an internal classification, not a client sign-off. | Changing weights changes who matches above 50%. | Do not assume the example is illustrative, and do not assume it is approved. | Matching | 7. Clarification or conflicting specifications | Client chooses the binding weight profile. Until then keep the live profile and do not copy readiness weights into it. | Client product owner
REQ-011 | Matching threshold, missing dates, inclusive overlap, category bonus, hard model compatibility, role compatibility, and self-match exclusion. | PDF page 6 shows a score and does not state 50%, missing-date behaviour, or a category bonus. | Handover sections 3–5 describe 50%, missing timeline score 0, inclusive overlap, category bonus capped at 1, and hard model mismatch. Handover is an internal briefing, not an approval. | defaults.ts POST_TO_POST_THRESHOLD 0.50; timelineFit in post-to-post-scoring.ts; candidate-generator timelineOverlap and collaborationModelCompatible; hard-constraints.ts passesPair; one-way.ts same-creator rejection. | These rules are implemented. Their client approval was not found. Missing dates can still pass the candidate overlap filter while scoring 0. | Unit tests exist and were not re-run in this review. | Directly affects UAT match or no-match outcomes. | Approval basis is undocumented. Behaviour is documented in code. | Matching; validation | 7. Clarification or conflicting specifications | Confirm each rule. Keep current behaviour during UAT closure unless a decision changes it. | Client product owner
REQ-012 | Party eligibility by relationship: B2B, B2P, P2B, P2P, including limited cases. | Detailed specification applicability tables. Mentorship section 2.3: B2B Limited, B2P Yes, P2B Yes, P2P Yes. Co-ownership 3.2: B2B Yes, B2P Limited, P2B No, P2P Limited. | No approval found for dropping limited B2B mentorship. | applicability-data.ts. Mentorship supportedRelationships are P2P, B2P, P2B only. professional_hiring is B2P and P2B and company-only creation. consultant_hiring includes B2B. Consortium, project_jv, spv, strategic_jv are company and B2B. | Most tables are represented. Mentorship B2B Limited is absent rather than limited. Co-ownership has no eligibility row. | Code inspection. | Company and individual UAT accounts follow these gates only where the registry is consulted. | Limiting individuals to three cards would remove creation of models they can use today. It does not, by itself, remove the right to respond to a company post. | Access; matching | 3. Partially implemented original requirement | Decide creation, response, group leadership, and acceptance separately for companies and individuals. | Client product owner
REQ-013 | Hiring distinguishes an employer demand, a company offering a role, professional expertise, and a professional seeking an engagement. | PDF page 3 need versus offer. Specification 4.1 Professional Hiring and 4.2 Consultant Hiring are separate sub-models. | Workbook Step3-Hiring A5 requires both sides on one company form and describes the company as offering compensation, while offer fields collect discipline and experience. | professional_hiring and consultant_hiring remain separate keys, commercial rules, and attribute sets. Compensation is a commercial component, not a second opportunity, in the current wizard. | Two hiring sub-models exist. The workbook's both-sides company form is not what the wizard does. | Code inspection. ISS-17 concerns consultant deliverables persistence. | High for company and individual UAT. | Two hiring needs must not match only because both selected Hiring. | UI; matching; commercial | 7. Clarification or conflicting specifications | Define four actor meanings and whether compensation is a commercial term or an Offer post. | Client product owner
REQ-014 | Cash capital contribution is distinct from Cash as an exchange mode. | Specification Project JV attributes include capital contribution and profit distribution. PDF Cash mode is a payment with milestones. | No amendment found. | PROJECT_JV_ATTRIBUTES capitalContribution plus allowedExchangeModes including cash. Commercial cash component is a payment structure. | Both concepts exist and can be confused in a single JV card. | Code inspection. ISS-04 equity publish path is separate. | ISS-04, ISS-06, ISS-15. | A flattened JV row that allows Cash can leak cash into SPV and Strategic JV, which currently exclude cash. | Commercial; domain/data | 2. Implemented but not sufficiently verified | Keep capital contribution and cash exchange as separate fields. Do not apply one JV commercial row to every JV sub-model. | Client product owner; commercial owner
REQ-015 | Model-specific commercial restrictions. | Derived from specification exchange applicability and implemented registry. PDF lists modes globally and also gives model examples. | Handover section 11 records the live matrix. Not a client approval. Workbooks propose a different matrix. | registry-data.ts allowedExchangeModes; allowed-components.ts. strategic_jv and spv exclude cash. bulk_purchasing and professional_hiring and competition_rfp exclude barter. task_based allows cash, hybrid, barter. | Restrictions are implemented per sub-model. | Code inspection. ISS-15 browser claim is historical, not repeated here. No dedicated strategic_jv cash-exclusion test was found. | ISS-15. | Workbook live JV row allows Cash and edge-case Barter for one JV card. | Commercial | 2. Implemented but not sufficiently verified | Preserve sub-model restrictions until an approved matrix replaces them. | Client product owner
REQ-016 | Indicative publication terms are not the binding negotiation or agreement terms. | PDF journey page 10 separates matching, negotiation, and agreement. Specification attributes are posting attributes. | ISS-13 asks whether a cash negotiation offer must include paymentSchedule before send. Unresolved. | Opportunity commercial validation versus packages/collaboration-models/src/exchange/value-exchange.ts cash requiredFields budget and paymentSchedule. validate-offer-terms.ts. | The two stages exist and use different shapes. Opportunity schedule is an array. Negotiation schedule is a required string. | Code inspection. Negotiation test covers a valid cash offer and a missing budget, not a missing schedule alone. | ISS-13. Open. | Workbook Step 4 optional bands do not answer ISS-13. | Commercial; validation; lifecycle | 7. Clarification or conflicting specifications | Naira decision on ISS-13, then acceptance criteria. Do not change the rule before that. | Client decision owner (Naira, as named in the handover)
REQ-017 | Publication requires readiness: all core required fields and score at least 80, from required ratio times 80 plus recommended ratio times 20. | Not in the January 2025 PDF. Implemented rule. | Workbook Step 5-Lists F6:F11 proposes 60/15/10/5/5/5. Not approved. | packages/collaboration-models/src/readiness/readiness-engine.ts evaluateReadiness and isPublishReady. opportunity-wizard-readiness.ts uses the same gate. | Current gate is implemented. Proposed formula is not. | Code inspection. Readiness tests exist and were not re-run. | Blocks publish during UAT. | Readiness is not the match score. Workbook bonuses must not be copied into match weights. | Validation; UI | 2. Implemented but not sufficiently verified | Keep 80/20 until a formula change is approved. If changed, define fairness for single-sided posts. | Client product owner; engineering
REQ-018 | Scheduled publication with timezone, revalidation, cancellation, and single execution. | Not in the January 2025 PDF or the detailed sub-model specification. | Workbook Step5 A112 S5-F13 and Step 5-Lists time lists. No approval found. | No schedulePublish implementation found under web/. server/ command route returns 501 and is not called by the SPA. | Not implemented. A date picker in a workbook is not an operational scheduler. | Code inspection. | Not an open ISS item. | Depends on a real backend and a worker. localStorage cannot reliably fire a future publish. | Operations; lifecycle | 8. Proposed change requiring scope confirmation | Treat as a proposed change. Do not estimate a delivery date until persistence and workers are in scope. | Client product owner; engineering
REQ-019 | Geography uses stable country and city identifiers. GeoNames is a recommendation, not a proven obligation. | Workbook Step1-Details A48 claims 195 ISO countries. A60 recommends GeoNames. PDF examples use Riyadh only. | No GeoNames contract or approval found. | web/src/domain/locations/canonical-locations.ts hierarchical ids. No GeoNames client in web/src. | Saudi-oriented canonical locations exist. Global GeoNames does not. | Code inspection. | Location fit uses coverage scopes. Nationwide Saudi coverage scores as full coverage for Saudi locations. | Workbook Cities column A has 198 entries including Other (not listed), so 197 named rows, not 195. Lists mix cities, regions, coasts, and projects. | Domain/data; matching | 8. Proposed change requiring scope confirmation | Approve the release-one country set and identifier scheme before any GeoNames integration. | Client product owner; engineering
REQ-020 | Member access versus field visibility, including commercial amount redaction and platform-controlled verified status. | PDF does not define field visibility. Workbook Step1-Details A112 says all posts are visible only to vetted subscribing members. Step 5 says the review is what matches see. | No approval found. Internal visibility module exists. | web/src/domain/opportunity-commercial-structure/visibility.ts showAmounts false for marketplace. entity-view-visibility.ts uses account status and verificationStatus, not a user-selected PMTwin vetted credential. | Redaction and teaser access exist. Workbook credential list includes PMTwin vetted as a selectable value. | Code inspection. | Affects what UAT users see on cards. | Selectable vetted status would conflict with platform verification. | Access; commercial; UI | 7. Clarification or conflicting specifications | Write a display contract: browse, view, respond, and which amounts are public, member-only, or party-only. | Client product owner; privacy owner
REQ-021 | Match lifecycle: Discovered, Accepted, Confirmed, Expired, Declined, Superseded. Close or archive expires discovered and accepted and leaves confirmed. Edits re-match when the fingerprint changes without rewriting accepted, confirmed, or negotiation history. | Not specified at this granularity in the January 2025 PDF. | Handover sections 6–7 and 18 say not to change accepted, confirmed, or negotiation semantics without approval. That is internal guidance. | packages/lifecycle manifest match states. expire-matches-on-opportunity-withdrawn.ts. matching-fingerprint.ts. opportunity-command-service maybeRematchAfterUpdate. Supersede is an explicit command. | Implemented as current product behaviour. | Code and tests exist. Not re-executed. Browser not re-run. docs/admin-portal.md still says there is no automatic re-match on edit, which is stale. | UAT close, archive, and republish behaviour. | Republish creates a new match rather than reopening the old one, per handover; code path should be re-checked in UAT if that sentence is used as acceptance. | Lifecycle; matching | 2. Implemented but not sufficiently verified | Do not change these transitions as a side effect of the wireframes. | Client product owner; engineering
REQ-022 | Agreement completion and contract completion. | Not in the January 2025 matching PDF. | Handover ISS-14: open business decision. No Naira confirmation found in the reviewed files. | deal-command-handler validateDealTransition has no active-contract block. lifecycle-orchestrator syncDealFromContract can move the linked agreement when a contract completes. | Independent completion is the current behaviour, with one-way sync from contract completion. | Code inspection. No test asserts a block while the contract is active. | ISS-14. Open. Not solved by the wireframes. | Current behaviour and the alternative are both coherent. Only the client can choose. | Lifecycle | 7. Clarification or conflicting specifications | Obtain the ISS-14 decision and write acceptance criteria before any code change. | Client decision owner (Naira, as named in the handover)
REQ-023 | VAT at 15% is explicit on financial fields. | Workspace KSA rule and ADR-104. Not a clause in the January 2025 PDF. | No client VAT acceptance record reviewed. | Cash commercial component has vatHandling. Profile UI references 15% Saudi VAT. Not every opportunity amount was shown to compute VAT. | Partial relative to the internal rule. | Not re-tested. | Commercial UAT. | Do not claim full VAT coverage. | Commercial | 3. Partially implemented original requirement | Confirm which amounts must show VAT during UAT closure. | Commercial owner; engineering
REQ-024 | Arabic RTL and Hijri-or-Gregorian dates. | Workspace KSA rule. PDF is English. Workbooks are English with some Arabic currency labels. | uat-findings-log UAT-30 classifies RTL as a manual gap. Not a client deferral approval. | No automated RTL suite under web/src was cited as passing in this review. | Requirement remains. Automated evidence was not found. | Not run. | Release acceptance for KSA. | Separate from matching wireframes. | UI; operations | 4. Original requirement not found in the reviewed implementation | Plan a manual RTL and date-format pass before production, not as part of an unapproved wireframe CR. | Engineering; QA
REQ-025 | Production backend, scheduled jobs, and cross-device persistence. | Internal BRD out-of-scope list defers payment settlement, binding signatures, full dispute automation, and external KYC. It does not say the marketplace stays on browser storage. | UAT-28 classifies localStorage as a known limitation. server/README states the API scaffold is not the active runtime. | web persistence is localStorage key pmtwin_web_overrides with demo and UAT prefixes. server POST /api/v1/commands returns 501. Web does not import the server client while the flag is off. | UAT is a browser-storage product. The scaffold is not the UAT backend. | README and source inspection. No deployment manifest reviewed. | Explains why scheduled publish and unique constraints are not operational. | Deployed UAT version not verified. | Operations | 7. Clarification or conflicting specifications | Separate UAT closure of the current SPA from production cutover. Do not treat HEAD as the deployed release. | Engineering; operations
WF-001 | Eight company cards: JV, Co-ownership, Resource Sharing, Resource Exchange, Bulk Purchasing, Task-based Collaboration, Hiring, Mentorship. No sub-model layer. | Company workbook Step2 A47 and A55:A62; Step 2-Lists M6:M13. Filename date 10 Aug 2026. File reviewed 3 Oct 2026. | No approval email, SOW clause, or change log was in the reviewed set. Walid email body was not supplied as a file. | Five families and 13 stored sub-models. Cards can be a view if each card maps to one or more retained keys. | Not implemented as the create step. collaboration-step still selects family and sub-model. | Code inspection. | Would change UAT create flow if adopted. | JV card would hide Consortium, Project JV, SPV, and Strategic JV unless they remain internal. Strategic Alliance and Competition/RFP have no card. | UI; domain/data; matching; commercial | 8. Proposed change requiring scope confirmation | Decide presentation versus domain replacement before design or build. | Client product owner
WF-002 | Three individual cards: Task-based Collaboration, Hiring, Mentorship. Types 3 and 4 marked not used. | Individual workbook Step 2-Lists B3:B4 and R6:R8. Sheet count inspected: 23. | No approval found. This would narrow creation relative to current applicability. | Individuals can currently relate to task, alliance, mentorship, equipment, resource, competition, and consultant hiring, among others. | Not implemented as a three-card limit. | Code inspection. | Changes who can post. Does not automatically remove response rights. | Participation, leading a group, and acceptance need separate answers. | Access; UI | 8. Proposed change requiring scope confirmation | Confirm creation rights and response rights separately. | Client product owner
WF-003 | Company model forms require both Need and Offer while Step 1 allows Need, Offer, or both. | Company Step1-Details A19:A23 versus Step3 introductions, including Step3-Hiring A5 and Step3-Cownr A5. | Conflicting specification inside the workbook. Not an approved rule. | Current wizard stores one intent per opportunity. | Conflict in the proposal, not in the live gate. | Workbook inspection. Formulas not recalculated. | Would block single-sided company posts if built as written. | Individual forms follow the selected side. Company forms say both required. | UI; validation | 7. Clarification or conflicting specifications | Define per model: single-sided, compulsory bilateral, or contribution plus requirement. | Client product owner
WF-004 | Resource Exchange both-sides post is labelled Multi-Party Match Type 4, and a detected chain is also Type 4. | Company Step 2-Lists Q9 and U9. L15 says the type columns are a proposed default. | Not approved. PDF Type 4 is a cycle of at least three parties. | detect-model does not upgrade a post to circular merely because both sides are filled. | Proposal conflicts with the original type definitions. | Workbook inspection. | A label must not be reported as a match or a higher score. | A two-party swap is two-way. Circular needs a real cycle. | Matching; UI | 8. Proposed change requiring scope confirmation | Keep type labels as eligibility hints only after the policy is approved. | Client product owner
WF-005 | Different-model Need and Offer should be two posts linked at Step 4, which would bypass hard model incompatibility. | Company Step1-Details A23. | Distinct from PDF page 4 linking, which does not say the posts may use different models. | collaborationModelCompatible rejects disjoint model or sub-model tokens. | Not implemented. | Code inspection. | Would change match outcomes for existing taxonomy. | Do not merge this with same-model multi-offer linking. | Matching | 8. Proposed change requiring scope confirmation | Explicit decision: may a barter link cross models, or must both posts share a model. | Client product owner
WF-006 | Commercial live matrix versus suggested matrix, including Custom activating every non-hidden mechanism while also saying no section is individually required. | Company Step 4-Lists F6:L13 live, N6:T13 suggested, N15. Commercial STR A142:A144. Step 4-Wireframe M18:M25. | Suggested matrix is marked not wired. N15 is copied into the individual workbook although those models are absent there. | allowed-components.ts is the live product matrix and does not match either workbook matrix. | Proposal and internal contradiction. | Formulas inspected, not recalculated. | Would change ISS-15 if cash is enabled on all JV forms. | M18:M23 activate Cash and Barter when Custom is on. M24:M25 then count their fields. That contradicts 'no section individually required'. | Commercial; validation | 7. Clarification or conflicting specifications | Approve one matrix by model and actor. Define Custom as selected components, not as prose. | Client product owner; commercial owner
WF-007 | Barter balance ratio divides an offer number by a USD midpoint of a need band. | Company Step 4-Lists AP6:AQ38 and AT9:AT11. Note at AP40. Wireframe C35 uses 0.85 to 1.15 as a label. | Not approved. Not a match-score weight. | No equivalent cross-currency ratio in the matching engine was reviewed as this formula. | Unsafe as specified: open bands and zero map to 0 or arbitrary midpoints; monthly and project totals share one table; currency is not converted. | Formula text inspected. Excel was not used to recalculate. | Informational only if ever shown. Must not become a score. | Free or goodwill has midpoint 0 and the ratio is defined as uncalculable. | Commercial; UI | 8. Proposed change requiring scope confirmation | Restrict the ratio to the same currency, unit, and period, or drop it from release one. | Commercial owner; engineering
WF-008 | Readiness 60% plus 15% dual declaration, 10% deliverables, 5% milestones, 5% value, 5% coverage. | Both workbooks Step 5-Lists E6:F11. | Not approved. Weights cell says they are editable. | readiness-engine.ts 80/20 and publish at 80 with all core required fields. | Not implemented. | Formula cells inspected, not recalculated. | Would change who can publish. | Individual INDEX/MATCH on Step 5-Lists Q6 spans rows 6 to 13 while only three models are listed in rows 6 to 8. | Validation; UI | 8. Proposed change requiring scope confirmation | Decide whether to change readiness. Do not reuse these weights as match weights. | Client product owner
WF-009 | Co-ownership card for real estate, companies, and assets, with SPV and Special Purpose Vehicle as separate entity options. | Step3-Cownr A26 and A38. Step 3-CO-Lists T6 and F14. | Extends specification 3.2, which is equipment and facilities, not a general company-stake product. Not approved. | No co_ownership key. | Not implemented as specified in the workbook. | Workbook inspection. | Could be confused with SPV and Project JV. | Duplicate labels will double-count if matching uses exact text. | UI; domain/data; commercial | 8. Proposed change requiring scope confirmation | Map the card onto retained JV or equipment keys, or approve a new key. Remove duplicate labels. | Client product owner
WF-010 | Company mentorship may target companies. Conditional text says Include individual professionals, which is not a dropdown value. | Step8-Mentorship A71. Specification 2.3 B2B is Limited, not a general company-to-company card. | Not approved. Implementation currently omits B2B entirely. | applicability-data.ts mentorship without B2B. | Three different rules exist: limited, absent, and proposed companies-only. | Code and workbook inspection. | Eligibility change. | Trigger text does not match Companies only / Individual professionals only / Both. | Access; UI | 7. Clarification or conflicting specifications | Choose one eligibility rule and one conditional value list. | Client product owner
ISS-01 | Consortium matches were not created when the partner was published after the lead. | Handover section 9, customer UAT list. Supporting email text is the handover's own draft, not an independent client file. | Handover marks VERIFIED after a browser pass. This review did not repeat that pass. | matching-service.ts rematchConsortiumLeadsAfterPartnerPublish; publish-matching.test.ts re-anchor case. | Code path exists. | Historical browser claim. Test not re-run. Not independently verified on 3 Oct 2026. | Open only if a new UAT run fails. | Do not reopen because the workbook uses a different group label. | Matching | 2. Implemented but not sufficiently verified | Keep the regression test in the UAT closure pack. | QA; engineering
ISS-02 | Company accounts could not open their own matches. | Handover section 9. | Marked VERIFIED in the handover. Not re-tested here. | entity-view-visibility.ts isMatchPartyViewer recognises partyId and actingForPartyId. entity-view-visibility.test.ts. | Code path exists. | Historical claim plus code inspection. Not re-executed. | Company UAT. | None found in the reviewed path. | Access | 2. Implemented but not sufficiently verified | Include a company-account open-match check in the final UAT script. | QA
ISS-03 | Company posts showed the employee name instead of the company. | Handover section 9. | Marked VERIFIED. Residual path noted in this review. | party-projection.ts companyDisplayNameForParty; match-detail-read-model resolveParticipantDisplayName. opportunity-details-read-model ownerPartyName still calls getPersonName(ownerPartyId). | Match display is corrected in the reviewed functions. Opportunity header path is not proven. | Code inspection. No browser check in this review. | Company UAT. | Possible residual on opportunity details. Not a reason to reject the earlier match-display fix. | UI; access | 2. Implemented but not sufficiently verified | Re-check the opportunity header with a company session during final UAT. | QA; engineering
ISS-04 | Equity opportunities could not be published. | Handover section 9. | Marked VERIFIED. Browser claim: Project JV equity 40% persisted. | packages/validation/src/business/budget.ts equity component on commercialStructure. validation.test.js Creation 3.0 equity case. | Validation reads current fields. | Test not re-run. Browser not repeated. | Commercial UAT. | None in the reviewed validator. | Commercial; validation | 2. Implemented but not sufficiently verified | Retain in regression. | QA
ISS-05 | Profit-sharing opportunities could not be published. | Handover section 9. | Marked VERIFIED. | budget.ts profit_sharing branch. validation.test.js. | Same pattern as ISS-04. | Not re-executed. | Commercial UAT. | None in the reviewed validator. | Commercial; validation | 2. Implemented but not sufficiently verified | Retain in regression. | QA
ISS-06 | Joint-venture Hybrid and Custom could not be saved. | Handover section 9. | Marked VERIFIED. Handover notes a single Custom component is represented as Hybrid. | budget.ts hybrid and custom completeness. legacy-migration.ts single custom becomes hybrid. | Save path exists. Hybrid representation of one Custom component is a rule choice. | Not re-executed. | Commercial UAT. | Confirm the single-Custom exception with the client if Custom is redefined by the workbook. | Commercial | 2. Implemented but not sufficiently verified | Keep current behaviour until Custom is redefined. | Client product owner; engineering
ISS-07 | Errors asked for fields that do not exist. | Handover section 9. | Marked VERIFIED. | collaboration-models validation uses registry labels. Profit-sharing publish copy was not re-read line by line in this pass. | Label source is the registry. | Registry test exists. No dedicated profit-sharing message test was identified. | Wizard UAT. | Verification is weaker than ISS-04. | Validation; UI | 2. Implemented but not sufficiently verified | Spot-check one profit-sharing empty publish during final UAT. | QA
ISS-08 | Revenue Sharing could not be chosen. | Handover section 9. | Marked VERIFIED. Revenue Sharing remains a component. | allowed-components.ts adds revenue_sharing when hybrid is allowed. | Selectable where the sub-model allows hybrid. | uat-one-way-findings.test.ts covers a hybrid component list. Not re-run. | Commercial UAT. | Workbook showing six choices does not create a sixth exchange mode. | Commercial | 2. Implemented but not sufficiently verified | Keep as a component. | Engineering
ISS-09 | Missing required details were reported only at the end. | Handover section 9. | Marked VERIFIED. | opportunity-wizard-page validateWizardStepAdvance runs sub-model attribute checks on the collaboration step. | Step gate exists. | create-validation.test.ts covers the create gate. A dedicated step-advance test was not identified. | Wizard UAT. | Workbook completeness counts are not a substitute for this gate. | Validation; UI | 2. Implemented but not sufficiently verified | Click through one incomplete collaboration step in final UAT. | QA
ISS-10 | The step indicator lost the current step when an error was shown. | Handover section 9. | Marked VERIFIED. | pm-form-stepper.tsx sets aria-current from the active step id, separate from error styling. | Code matches the intended fix. | pm-form-state.test.ts covers error status, not aria-current. Browser not re-run. | Wizard UAT. | Accessibility behaviour should be seen once in the browser. | UI | 2. Implemented but not sufficiently verified | One manual stepper check in final UAT. | QA
ISS-11 | A deal could not move past negotiation because Create Commercial Agreement was missing. | Handover section 9. | Marked VERIFIED. | create-commercial-agreement-ui-actions.ts canShowCreateCommercialAgreementFromNegotiation. | Action is available when the workflow says so. | create-deal-ui-actions.test.ts. Not re-run. Browser not re-run. | Deal UAT. | None found in the reviewed function. | Lifecycle; commercial | 2. Implemented but not sufficiently verified | Retain in the deal-flow script. | QA
ISS-12 | Contracts could not be completed because Complete Contract was missing. | Handover section 9. | Marked VERIFIED. | contract-detail-read-model canCompleteContract; complete-contract-ui-actions.ts. | Action exists on the contract page path reviewed. | complete-contract-ui-actions.test.ts. Not re-run. | Contract UAT. | Distinct from ISS-14. | Lifecycle | 2. Implemented but not sufficiently verified | Retain in the contract script. | QA
ISS-13 | A cash negotiation offer requires a payment schedule. | Handover sections 9, 14, and 17. Question addressed to Naira. No reply was in the reviewed files. | Open business decision. Not a wireframe defect. | value-exchange.ts cash requiredFields include paymentSchedule. validate-offer-terms.ts enforces the group. | The requirement is implemented and still mandatory. | Test shows a valid offer includes the field. It does not assert the missing-schedule error alone. | Open UAT decision. | Workbook payment timing does not decide this. | Commercial; validation | 7. Clarification or conflicting specifications | Wait for the decision. Then change code only if the decision says the schedule may wait. | Client decision owner (Naira)
ISS-14 | An agreement can be completed while the related contract is still active. | Handover sections 9, 15, and 17. No decision found. | Open business decision. | No active-contract guard on agreement completion. Contract completion can sync the linked agreement to completed. | Current behaviour allows independent completion and one-way sync. | Sync tests exist. No mutual-exclusion test. Not re-run. | Open UAT decision. | Do not implement a block without the decision. | Lifecycle | 7. Clarification or conflicting specifications | Wait for the decision and record acceptance criteria. | Client decision owner (Naira)
ISS-15 | Strategic JV could not be published with any payment type. | Handover section 9. | Marked VERIFIED. Cash is intentionally not offered. | strategic_jv allowedExchangeModes equity, profit_sharing, hybrid. allowed-components derives the picker. | Exclusion of cash is present. Publish of equity depends on the equity validator. | No dedicated strategic_jv exclusion test found. Browser claim not repeated. | Commercial UAT. | A single JV workbook row must not put Cash back on this sub-model without approval. | Commercial | 2. Implemented but not sufficiently verified | Keep the exclusion. Add a regression assertion when the commercial matrix is next touched. | Engineering; QA
ISS-16 | Tag fields removed spaces and commas while typing. | Handover section 9. | Marked VERIFIED. | dynamic-form-renderer.ts parseTagsInput keeps a trailing separator. dynamic-form-renderer.test.ts. | Typing behaviour is implemented in the parser. | Unit test exists. Not re-run. Browser not re-run. | Wizard UAT. | None in the reviewed parser. | UI | 2. Implemented but not sufficiently verified | Retain the test. | Engineering
ISS-17 | Consultant Hiring deliverables were ignored on save. | Handover section 9. | Marked VERIFIED. Handover says the review counter counts structured scope deliverables, so zero there can be expected. | draft-model.ts preserves tag deliverables. draft-model.test.ts consultant hiring case. | Attribute save path exists. | Unit test not re-run. Browser not re-run. | Hiring UAT. | Do not treat a zero scope counter as a failed save without checking the attribute. | Domain/data; UI | 2. Implemented but not sufficiently verified | Final UAT should reload the consultant record and read the tag field. | QA
WB-001 | Duplicate individual specifications inside the company workbook use different field IDs from the individual workbook. | Company Step8-Mentorship-Ind O01 is domain. Individual Step3-ind-mentor O00 is intent and O01 is domain. Same shift on task-based sheets. | No version stamp says which copy is authoritative. | Not implemented. | Specification defect. | Cell inspection. | Would cause the wrong field to be required. | IDs are shifted, not merely renamed. | Domain/data | 7. Clarification or conflicting specifications | Pick one schema and map the other. Do not implement both. | Client product owner; business analyst
WB-002 | Conditional text does not match dropdown values. | Step8-Mentorship A71 trigger Include individual professionals. Individual task N00 text uses the same phrase while values are Companies only / Individual professionals only / Both. | Internal contradiction. | Not implemented. | Specification defect. | Cell inspection. | A condition that never matches will hide required fields. | Use option IDs in conditions. | UI; validation | 7. Clarification or conflicting specifications | Correct the workbook before build. | Business analyst
WB-003 | SPV and Special Purpose Vehicle appear as separate options. | Step3-Cownr A38. Step 3-JV A120. Step 3-CO-Lists T6. | Duplicate labels. | Registry has one spv key. | Specification defect. | Cell inspection. | Exact-text matching would split one legal form. | One identifier, two display languages if needed. | Domain/data | 7. Clarification or conflicting specifications | Collapse to one option. | Business analyst
WB-004 | Arabic & English is one language value. PMTwin vetted is a user-selectable credential. | Individual and company mentorship credential and language lists, for example Step8-Mentorship-Ind language values. | Conflicts with platform-controlled verification. | Verified status is derived from the account, not from this dropdown. | Specification defect if built literally. | Cell inspection. | Combined language value cannot be queried as Arabic and as English. | Split languages. Remove self-serve vetted, or rename it to a claim. | Domain/data; access | 7. Clarification or conflicting specifications | Correct lists before build. | Business analyst; privacy owner
WB-005 | Company-only commercial note is copied into the individual workbook. | Individual Step 4-Lists N15 repeats the Co-ownership, Bulk Purchasing, and Mentorship equity changes. | The individual live matrix is only three models. | Not the product matrix. | Copy error. | Cell inspection. | Readers may think individuals have co-ownership commercial rules. | Delete or replace the note. | Commercial | 7. Clarification or conflicting specifications | Correct the individual workbook. | Business analyst
WB-006 | Individual review routing formula spans eight company rows. | Individual Step 5-Lists Q6 indexes C6:C13 and matches B6:B13. Only B6:B8 are individual models. | Copied range. | Not product code. | Latent specification defect. | Formula inspected, not recalculated. | May resolve today and fail when rows change. | Point the formula at the three individual rows. | UI | 7. Clarification or conflicting specifications | Correct before any prototype is treated as logic. | Business analyst
WB-007 | Geographic count and place types are inconsistent. | Step1-Details A48 says 195 countries. Cities column A has 198 values including Other (not listed). Narrative cities include NEOM, Qassim, North Coast, and New Administrative Capital. | GeoNames is recommended at A60, not integrated. | Canonical location IDs in web are not this sheet. | Reference-data defect. | Row count from openpyxl. Formulas not recalculated. | Location fit would be unstable on these labels. | Separate country, region, city, coast, and project. | Domain/data | 7. Clarification or conflicting specifications | Replace free-text lists with identifiers. | Business analyst; engineering
WB-008 | Prototype gates use completeness counts rather than server validation. | Step 4-Wireframe M24:M27 and model wireframe gates. | COUNTA-style checks do not prove numeric, date, or conditional validity. | Product publish validation is in packages/validation and the wizard gate. | Workbook is not the server. | Formulas inspected, not recalculated. No stored Excel error cells were used as proof. | UAT must use the application, not the workbook gate. | Do not accept a green workbook cell as a passed publish. | Validation | 7. Clarification or conflicting specifications | Keep publish rules in the application. | Engineering; QA

## Decisions
ID | Decision | Why it blocks closure | Proposed owner role | Current evidence
D-01 | Are eight company cards and three individual cards a new presentation over the stored 13 sub-models, or a replacement of those sub-models? | Matching treats model and sub-model mismatch as a hard failure. Removing keys changes history. | Client product owner | Step2 A47; registry-data.ts
D-02 | What happens to Consortium, Project JV, SPV, Strategic JV, Strategic Alliance, and Competition/RFP? | They have distinct commercial and eligibility rules. No card names them except as examples or entity options. | Client product owner | registry-data.ts; Step2 A55
D-03 | Which commercial matrix is binding, and does one JV row apply to SPV and Strategic JV? | Those sub-models currently exclude Cash. | Client product owner; commercial owner | Step 4-Lists F6:L13 and N6:T13; allowed-components.ts
D-04 | May a company post be need-only or offer-only? | Step 1 allows it. Company Step 3 forms say both sides are required. | Client product owner | Step1-Details A19:A23
D-05 | Do individuals lose the right to create models outside three cards, and do they keep the right to respond, lead, and accept? | Current applicability is wider than three cards. | Client product owner | Individual Step 2; applicability-data.ts
D-06 | Is the PDF score example the binding formula? | Live weights differ. No approval of either profile was found. | Client product owner | PDF page 6; defaults.ts; UAT-26
D-07 | Are 50% threshold, missing-date score 0, inclusive overlap, category bonus, hard incompatibility, and self-match exclusion accepted? | They decide match and no-match. They are implemented without a client approval record. | Client product owner | Handover sections 3–5; matching source
D-08 | May a barter link cross collaboration models? | Original linking does not say yes. Current engine says no. | Client product owner | PDF pages 4 and 9; Step1-Details A23
D-09 | What does Custom require at publish? | Workbook prose and wireframe formulas disagree. Code maps a lone Custom component to hybrid. | Client product owner | Commercial STR A142; wireframe M18:M25
D-10 | ISS-13: is payment schedule mandatory before a cash negotiation offer is sent? | Code requires it. Handover says not to change it until Naira decides. | Client decision owner (Naira) | value-exchange.ts; handover sections 14 and 17
D-11 | ISS-14: may an agreement be completed while the related contract is active? | Code allows it and can sync the agreement when the contract completes. | Client decision owner (Naira) | deal and contract handlers; handover section 15
D-12 | Is scheduled publish in the UAT scope? | No executor exists. It needs a backend worker. | Client product owner; engineering | Step5 S5-F13; server README
D-13 | Which fields are hard filters, score factors, preferences, or informational? | New dropdowns must not become hard filters by accident. | Client product owner | Workbook lists; hard-constraints.ts
D-14 | Which markets, currencies, and place types are in release one, and is GeoNames required? | Workbook geography is inconsistent. GeoNames is only recommended. | Client product owner | Cities sheet; Step1-Details A48:A60
D-15 | Which commercial amounts may a counterparty see before negotiation? | Marketplace redaction exists. Workbook visibility sentences conflict. | Client product owner; privacy owner | visibility.ts; Step1 A112; Step5 A3

## CR reassessment
ID | Previous package | This review | Evidence | Original completion versus proposed change | Prerequisite decisions | Technical impact | Migration risk | Effort range (person-days) | Confidence
CR-01a | CR-01 UI portion of the guided 8/3 wizard | Retain as a proposed UI change. Withdraw any implication that it is already approved. | 30 Sep review table 4 CR-01 split presentation from taxonomy. No effort figure was in that document. | Proposed enhancement. The five-step journey already exists. | D-01, D-02, D-04, D-05 | UI | Low if stored keys do not change. | 8–15 | Medium, after the mapping is frozen
CR-01b | CR-01 taxonomy replacement | Retain as a separate core decision. Do not start it under the UI estimate. | Step2 A47 says there is no sub-model layer. Hard incompatibility uses subModelType. | Proposed domain replacement, not original completion. | D-01, D-02, D-03, D-05 | Domain/data; matching; commercial; lifecycle | High. Existing opportunities, matches, agreements, and contracts keep old keys. | 25–45 build, plus 10–20 migration, only after decisions | Low until D-01 is answered
CR-02 | Co-ownership and pool details | Split. Original section 3.2 completion is not a new paid CR by default. Real-estate, company-stake, booking, and settlement scope is proposed. | Specification 3.2; equipment_sharing attributes; Step3-Cownr. | Original completion for the equipment record. Proposed extension beyond it. | D-01, D-02, D-09 | Domain/data; matching | Medium if a new key is added. Low if fields hang off equipment_sharing. | Original record 8–14. Proposed extension 12–25. Booking or settlement excluded. | Medium
CR-03 | Matching normalization and topology | Retain. Separate original four-type completion from new hard filters. | PDF pages 5–9; detect-model.ts; Step 2-Lists type labels. | Partly original completion, partly proposed policy. | D-06, D-07, D-08, D-13 | Matching | High if hard filters or weights change, because historical matches will not be recomputed the same way. | Original adapter work 8–15. Policy change 10–20. Regression 5–8. | Low until field roles are assigned
CR-04 | Commercial matrix and Custom | Retain as a decision, not as approved scope. Keep current sub-model restrictions meanwhile. | Step 4 matrices; Commercial STR A142; allowed-components.ts. | Proposed change where it differs from the registry. Original modes already exist. | D-03, D-09, D-10 | Commercial; validation | Medium. Agreements already store components. | 6–12 after one matrix is approved. Not chargeable until then. | Medium
CR-05a | Geography identifiers, split from CR-05 | Retain as data work for release one. The 30 Sep review had one CR-05. | Cities 198 rows; canonical-locations.ts. | Partly original location matching, partly new global coverage. | D-14 | Domain/data; matching | Medium if stored location strings change. | 8–14 | Medium
CR-05b | GeoNames integration | Withdraw from the UAT baseline. It is a recommendation in Step1-Details A60, not an implemented or approved integration. | No GeoNames client in web/src. | Proposed enhancement. | D-14 | Operations | Low if not started. | 10–18 only if approved. Otherwise zero. | Medium
CR-05c | Access and field visibility | Retain as a policy decision. Some redaction already exists. | visibility.ts; Step1 A112; credential lists. | Clarification plus possible enhancement. | D-15 | Access; commercial; UI | Low if limited to display rules. | 5–10 | Medium
CR-06 | Readiness formula 60/15/10/5/5/5 | Retain as proposed. Do not replace the 80/20 gate without approval. | Step 5-Lists F6:F11; readiness-engine.ts. | Proposed change. Current gate is implemented. | D-04 | Validation; UI | Medium. Previously published drafts used another score. | 5–10 after the formula and single-sided fairness are decided. | Medium
CR-07a | Scheduled publish | Retain as a separate proposed feature. The 30 Sep review said CR-07 should be split and gave no estimate. | Step5 S5-F13. No scheduler in web/. Server commands return 501. | Proposed enhancement. Not original PDF scope. | D-12 and a persistence decision | Operations; lifecycle | High if it must survive browser shutdown. | 15–30 only with a backend worker. Not credible on localStorage alone. | Low
CR-07b | Same-model need linked to multiple offers | Reclassify as original completion, not a new CR, if the January PDF is accepted as binding. | PDF pages 4 and 9. No offer register in the reviewed wizard. | Original requirement not found as a user feature. Discovery of many candidates already exists. | D-08 must stay same-model | UI; domain/data; matching | Medium. | 8–15 | Medium
CR-07c | Cross-model barter link | Retain as a proposed policy change. Do not bundle it with CR-07b. | Step1-Details A23 versus collaborationModelCompatible. | Proposed change. | D-08 | Matching | High. It weakens a hard constraint. | 10–20 including regression, only after D-08 is yes. | Low until decided
ISS-13 | Cash negotiation payment schedule | Keep as an open decision. Do not fold it into the wireframe CR list. | value-exchange.ts; handover section 14. | Existing rule awaiting confirmation or a small change. | D-10 | Validation; commercial | Low. | 1–3 after the decision. | High
ISS-14 | Agreement completion while a contract is active | Keep as an open decision. | deal and contract lifecycle. Handover section 15. | Existing rule awaiting confirmation or a small change. | D-11 | Lifecycle | Medium if historical agreements must be reinterpreted. | 2–5 after the decision. | High

## Model mapping
Original name | Where named | Stored key today | August 2026 card | Preserve internally? | Notes
Task-Based Engagement | Spec 1.1; PDF task example | task_based | Task-based Collaboration | Yes | Card can rename the key. Bilateral compensation is a proposal.
Consortium | Spec 1.2; PDF group example | consortium | Only inside JV examples | Yes, until retired by decision | Company and B2B. Topology consortium.
Project-Specific Joint Venture | Spec 1.3 | project_jv | JV card | Yes | Allows cash and equity. Capital contribution is separate from cash mode.
Special Purpose Vehicle | Spec 1.4 | spv | JV entity option and Co-ownership entity option | Yes | Company only. Cash excluded. Workbook duplicates the label.
Strategic Joint Venture | Spec 2.1 | strategic_jv | JV card | Yes | Cash excluded. ISS-15.
Long-Term Strategic Alliance | Spec 2.2 | strategic_alliance | No card | Yes | Do not drop by omission.
Mentorship Program | Spec 2.3 B2B Limited | mentorship | Mentorship | Yes | Code omits B2B. Workbook proposes company targets.
Bulk Purchasing | Spec 3.1 | bulk_purchasing | Bulk Purchasing | Yes | Barter excluded in code. Suggested matrix adds an edge case.
Co-Ownership Pooling | Spec 3.2; PDF page 8 | No key. Partial equipment_sharing | Co-ownership | Do not invent a retirement | Original gap plus a wider proposed card.
Resource Sharing and Exchange | Spec 3.3 one sub-model | resource_sharing and equipment_sharing | Resource Sharing and Resource Exchange | Yes, both keys | The split already happened in code. A second split needs a map.
Professional Hiring | Spec 4.1 | professional_hiring | Hiring card | Yes | Company creation. B2P and P2B. Cash and hybrid.
Consultant Hiring | Spec 4.2 | consultant_hiring | Hiring card | Yes | Includes B2B and barter. Do not merge validation with professional hiring without a decision.
Competition / RFP | Spec 5.1 | competition_rfp | No card | Yes | Do not drop by omission.
Equipment Sharing | Not a separate spec sub-model | equipment_sharing | Folded into Resource Sharing or Co-ownership by interpretation | Yes | Added in implementation. Not a spec retirement of co-ownership.